## Sheet1
2001-07-31
TMS
PREPARATION FOR PRELIMINARY DESIGN REVIEW - IMPACT
ITEM | ITEMS FROM CONTRACT DELIVERABLES LIST | NEEDED FOR PDR | STATUS
1 | Monthly Technical Progress Reports
2 | Monthly and Quarterly NASA Financial Reports
3 | Preliminary Design Review Data Package | Yes | Largely extracted from peer review materials
4 | Critical Design Review Data Package
5 | Instrument Pre-Environmental Review Data Package
6 | Pre-Environmental Review Data Package
7 | Instrument Pre-Ship Review Data Package
8 | Pre-Ship Review Data Package
9 | Program Schedule and Progress Information
10 | Final Product Assurance Implementation Plan | Yes, Signed Off | In negotiation; issue is CESR parts
11 | Final Configuration Management Plan | Yes, Approved | Draft submitted, Project wants more
12 | Documentary Photographs
13 | Final Report
14 | Performance Specification for IMPACT | Yes, Instrument Requirements Matrix | Draft Performance Requirements pemding top level requirements to add flow-down
15 | Preliminary Thermal and Structural Analytical Models & Report | Yes, Analysis Results included in PDR Presentation | Data provided to APL. Analysis in progress
Final Thermal and Structural Analytical Models
16 | Preliminary Failure Modes and Effects Analysis | Yes, Project Providing, Need to incorporate reliability into PDR Presentation | Waiting for a request for information; what are you looking for?
Final Failure Modes and Effects Analysis
17 | Draft Environmental Test Plan | Yes, Approved, Should include Test Verification Matrix for PDR Presentation | Draft Verification Matrix in Peer Review presentation
Final Environmental Test Plan
18 | Final Environmental Verification Matrix
19 | Draft Physical Block Diagram | Yes, In PDR presentation | To what level? There is a functional block diagram in the peer review presentation
Final Physical Block Diagram
20 | Draft Grounding Diagram | Yes, For EMI Peer Review the end of August and PDR presentation | Draft already provided. Updated draft in peer review presentation.
Final Grounding Diagram
21 | IMPACT Proto-Flight Model
22 | IMPACT Flight Model
23 | Preliminary Parts Identification List | Yes | In progress (CESR already provided)
Final Parts Identification List
24 | Preliminary Hazardous Materials List | Yes | In progress
Final Hazardous Materials List
25 | Preliminary Materials and Processes List | Yes | In progress (CESR already provided)
Final Materials and Processes List
26 | Printed Wiring Board Coupons
27 | Preliminary Instrument Flight/Ground Software Development and Management Plan | Yes | SEP Draft Plan delivered
Final Instrument Flight/Ground Software Development and Management Plan
28 | Mechanical Ground Support Equipment
29 | Electrical Ground Support Equipment
30 | Proto-flight Data Acceptance Package
31 | Flight Data Acceptance Package
32 | IMPACT Instrument to S/C Integration Procedure
33 | Plan for Data Processing | Not required. Include reqmts in Instr Reqmts Matrix. Put ground system design in S/W Dev Plan
34 | Preliminary Experiment Users Manual
Final Experiment Users Manual
ITEM | ITEMS NOT IN DELIVERABLES LIST | NEEDED FOR PDR PRESENTATION | STATUS
1 | Work Breakdown Structure | Yes, Project Providing | Will send to IMPACT the week of 07/30/2001.
2 | Integration & Test Flow | Yes, Include Test Facilities | Draft in peer review presentation
3 | Top-Level Schedule | Yes, showing top level events for major suite elements | We have several detailed low-level schedules and top level milestone schedules through which they are linked.
4 | Concept of Operations | Yes, Providing overview of isntrument on-orbit operation scenario
5 | Concept Test Results | Results of pre-PDR concept testing, Boom Deployments?
6 | Risk Items | Address top ten risk items, mitigation plans, mitigation schedule. | First risks evaluated and submitted. Require periodic re-evaluation