## Sheet1
No. | Risk Item | Score | Mitigation |  |  | Mitigation Schedule
|  |  |  | PDR | CDR | Bread-board Test | Sub-system Test | System Test | Env test | Early Orbit Test
I-1 | Improper S/C operation up to loss of mission if any non-redundant component fails. | MEDIUM | •Failure Modes and Effects Analyses determine consequences of non-redundant component failures. •Probabilistic Risk Analysis to determine areas where additional redundancy is required. •Fault Tree Analyses (Early and Updated) determine root causes and aid in contingency test planning. | MEDIUM | MEDIUM | MEDIUM | MEDIUM | MEDIUM | MEDIUM | LOW
I-2 | Large instrument suites may be late in delivery. | MEDIUM | •Have requested additional instrument managers from Code 700. Contractors will be utilize if no civil servants are available. | MEDIUM | LOW | LOW | LOW | LOW | LOW | LOW
I-3 | Electrical interference with the SWAVES antennas causing degradation of SWAVES science. | LOW | •STEREO EMC Control Plan and EMI Performance Requirements Specification is the governing design document for all mission elements. •STEREO EMI/EMC/Magnetics Committee established to review all related design, implementation, and test issues for all mission hardware. | LOW | LOW | LOW | LOW | LOW | LOW | LOW
I-4 | Decreases margins at Observatory level | MEDIUM | •Contingency levels maintained based on AIAA standards. •Resources tracked by STEREO Project. •Contingency is held at the observatory level. A formal mass/power reporting system has been established. | MEDIUM | MEDIUM | MEDIUM | LOW | LOW | LOW | LOW
I-5 | Magnetic field generation by the S/C will degrade Magnetometer performance. | LOW | •The STEREO EMI/EMC Control Plan includes requirements and guidelines for magnetic cleanliness design. Prior to delivery, a STEREO Magnetics Engineer will inspect any components capable of generating a magnetic field. | LOW | LOW | LOW | LOW | LOW | LOW | LOW
I-6 | STEREO instruments are sensitive to contamination by dust or particulates and by hydrocarbon vapors and liquids. | LOW | •Contamination committee has been formed. Includes representatives from each Instrument, Spacecraft, and Project Office. •Contamination Control Plan is process addressed requirements and methodology to control contamination on the ground. Handling and cleaning procedures have been presented to instrumenters and spacecraft during Phase A. •Design guidelines and requirements provided to team in Observatory Contamination Control Plan. •Contamination requirements subject during design review at vendors. Subsystem reviews and Observatory level reviews. | LOW | LOW | LOW | LOW | LOW | LOW | LOW
I-7 | Delay on instrument deliveries could cause project schedule delays. | LOW | •Foreign Contributor have confirmed funding for STEREO. -Major contributors are experienced NASA partners. -Additional schedule contingency for foreign partners due to early funding foreign government agencies. | LOW | LOW | LOW | LOW | LOW | LOW | LOW
I-8 | Delay of equipment and information import/export could cause project schedule delays. | LOW | •An Export/Import Plan is being developed. •All six Letters of Agreement have been concluded: Germany, France, UK, Hungary, ESA, Switzerland. •Equipment exports are under four year duration: No License Required. •Technical Data will be exported in compliance with ITAR | LOW | LOW | LOW | LOW | LOW | LOW | LOW
I-9 | Stray light from external sources may degrade HI images. | MEDIUM | •Pre-PDR stray light testing of HI breadboards is being performed. Further testing will be completed during phase C. Optical testing of stray light from SWAVES antennas into HI FOV is being performed (May 2001). | MEDIUM | MEDIUM | MEDIUM | LOW | LOW | LOW | LOW
I-10 | COR1 Optical design has not been flown in space. | MEDIUM | •Validate design early in program. •Primary risk is unacceptably large levels of stray light. •Significant environmental testing is being performed on critical components during phase B and into implementation. | MEDIUM | MEDIUM | MEDIUM | MEDIUM | LOW | LOW | LOW